## Sheet1
JANM
Identified by: Reported To: Date: Environment Details:
BugID | Expected Result | Bug Description | Steps To Reproduce | Severity | Priority | Screenshot | Status
DEF_JANM_01 | Should work all menu's under hamburger menu | All menu's under hamburger is not working | 1.open website 2.click hamburger | critical |  |  | New
DEF_JANM_02 | Should view the bio of doctor | Doctor bio view is not working | 1.open website 2.click the view bio | major |  |  | New
DEF_JANM_03 | Good to have appointment option | Book appointment is not working | 1.open website 2.click Book Appointment | enhancement |  |  | New
DEF_JANM_04 | Should display 'view all services' | View all services not working | 1.open website 2.click Book Appointment | major |  |  | New
DEF_JANM_05 | social media icons should work (direct properly) | social mdia icons not working | 1.open website 2.click social media icons | major |  |  | New
DEF_JANM_06 | Alignment of the website should be as per standard | Alignment from top to bottom is improper | 1.open website 2.scroll | major |  |  | New
DEF_JANM_07 | Instagram statement can be an icon to redirect | instagram statement is not icon and does not redirect | 1.open website 2.scroll down to bottom 3.click instagram | enhancement |  |  | New
DEF_JANM_08 | details of spine in 'Our service' should be inside box | details of spine in 'Our service' is outside box | 1.open website | major |  |  | New
DEF_JANM_09 | Text and images should not overlap | Text and images overlap each other | 1.open website | major |  |  | New
DEF_JANM_10 | Navigation bar should be there for desktop/web view | There is no navigation bar for web view but contain hamburgermenu | 1.open website 2.check for navigation bar | critical |  |  | New
DEF_JANM_11 | Should be responsive in mobile view | Some of the images are not responsive | 1.open website 2. check site on different devices | major |  |  | New
DEF_JANM_12 | Font and font size should be as per standard | Font and font size is different | 1.open website 2.check font and font size | enhancement |  |  | New
DEF_JANM_13 | Contact number should be redirect to call | Contact number does not redirect | 1.open website 2.click on contact number | major |  |  | New
DEF_JANM_14 | Country code is not present for contact number | Does not contain country code | 1.open website | minor |  |  | New
DEF_JANM_15 | map zoom option should be working(resolution:1920*1080) | map zoom option not working | 1.open website 2.click on zoom'+''-' icons on map | minor |  |  | New
DEF_JANM_16 | can provide back to top icon/button | back to top icon/button not present | 1.open website 2.check for back to top icon/buttoon | enhancement |  |  | New
DEF_JANM_17 | Site should be secured | site is not secured | 1.open website 2.check site security | critical |  |  | New
DEF_JANM_18 | Website logo should be there | website logo is absent | 1.open website 2.check for logo | enhancement |  |  | New
DEF_JANM_19 | all images should be of high quality | some of the images lack quality | 1.open website 2.check all images | minor |  |  | New
DEF_JANM_20 | When hamburger menu is clicked footer should not get affected | When hamburger menu is clicked footer get break out | 1.open website 2.click hamburgermenu 3.check footer | major |  |  | New
DEF_JANM_21 | menu icon when clicked should not break icon | When menu icon clicked should not break icon break out | 1.open website 2.click hamburger menu | major |  |  | New
DEF_JANM_22 | Content should not be different | contents of brain and pain have same contents | 1.open website 2check contents | major |  |  | New
DEF_JANM_23 | same topic repeated | Our surgeon heading repeated twice | 1.open website 2.scroll down to our surgeon | major |  |  | New
DEF_JANM_24 | Address should be same on map | address is different from map address | 1.open website 2.check map address | major |  |  | New
DEF_JANM_25
DEF_JANM_26
DEF_JANM_27
DEF_JANM_28
DEF_JANM_29
DEF_JANM_30
DEF_JANM_31
DEF_JANM_32
DEF_JANM_33
DEF_JANM_34
DEF_JANM_35
DEF_JANM_36